## Dashboard
Connected Enterprise ¦ Pending Activity Overview
30-task cross-project starter list: Connected Enterprise, Project QSR, and Smart Factory. Update the Activity Tracker fields as work progresses.
|  |  |  | Status | Count | Project | Count
Total Activities | Pending / Open | In Progress | Blocked | Pending | 30 | Connected Enterprise | 10
30 | 30 | 0 | 0 | In Progress | 0 | Project QSR | 10
|  |  |  | Blocked | 0 | Smart Factory | 10
|  |  |  | On Hold | 0
Estimated Days | Estimated Hours | Remaining Hours | Overdue | Completed | 0
139 | 1112 | 1112 | 0
Tracking note
Estimates and dates are indicative planning values. Update Owner, Status, Actual Hours, and Due Date to keep the tracker current.

## Activity Tracker
Pending Activities Tracker
Imported from PROJECT_TASK_PLAN.csv. Edit the tracker fields to keep the plan current.
Task ID | Project / Section | Activity | Description | Type | Priority | Complexity | Status | Owner | Start Date | Due Date | Est. Days | Est. Hours | Actual Hours | Remaining Hours | Days Left | Overdue? | Dependencies | Notes / Backend Data
CI-001 | Connected Enterprise ¦ Cost Insights | Cost Insights - Real-time Data Integration | Connect cost data to live backend updates and refresh KPI cards and charts without manual reload. | UI + Backend | High | High | Pending |  | 2026-09-07 | 2026-09-11 | 5 | 40 |  | 40 | 9 | No | C-001 | Live cost endpoint or SSE/polling; spend, savings, and utilization updates
AI-001 | Connected Enterprise ¦ Ask AI | Ask AI Enhancement - Contextual Answers & Citations | Improve prompts, add current-page context, citations, and clearer loading and error states. | UI + Backend | High | High | Pending |  | 2026-09-07 | 2026-09-14 | 6 | 48 |  | 48 | 12 | No | None | Context payload, response metadata, and feedback capture
UI-001 | Connected Enterprise ¦ Overall UI | Overall UI Improvements - Consistency & Accessibility | Standardize spacing, typography, empty states, buttons, responsive layouts, keyboard access, and focus behavior. | UI | High | Medium | Pending |  | 2026-09-14 | 2026-09-18 | 5 | 40 |  | 40 | 16 | No | None | Shared components, design tokens, responsive and accessibility checks
GWT-001 | Connected Enterprise ¦ Gateway Twin | GW Twin UI - Digital Twin View | Build a gateway digital-twin view with topology, component health, metrics, and drill-down panels. | UI | High | High | Pending |  | 2026-09-14 | 2026-09-22 | 7 | 56 |  | 56 | 20 | No | None | Gateway component inventory, health metrics, and topology payload
DEV-001 | Connected Enterprise ¦ Devices | Real-time Device Telemetry Experience | Surface live device health and telemetry with last-seen, connectivity, and refresh indicators. | UI + Backend | High | Medium | Pending |  | 2026-09-21 | 2026-09-25 | 5 | 40 |  | 40 | 23 | No | None | Device telemetry stream, last-seen timestamps, and connection state
INC-001 | Connected Enterprise ¦ Incidents | Live Incident & Alert Feed | Replace mock incident updates with live events, severity filters, acknowledgement state, and timestamps. | UI + Backend | High | Medium | Pending |  | 2026-09-21 | 2026-09-24 | 4 | 32 |  | 32 | 22 | No | None | Incident event stream, severity, acknowledgement, and audit fields
POL-001 | Connected Enterprise ¦ Policy Management | Policy Management UX Refresh | Simplify create and edit flows, inline validation, bulk actions, and persisted enable or disable state. | UI | Medium | Medium | Pending |  | 2026-09-28 | 2026-09-30 | 3 | 24 |  | 24 | 28 | No | None | Reusable form patterns, validation rules, and bulk-action states
TOP-001 | Connected Enterprise ¦ Topology | Network / Branch Topology Visualization | Add interactive branch-to-gateway topology with status colors and quick navigation. | UI + Backend | Medium | High | Pending |  | 2026-09-28 | 2026-10-05 | 6 | 48 |  | 48 | 33 | No | GWT-001 | Branch, gateway, tunnel, and link-status relationships
RPT-001 | Connected Enterprise ¦ Reporting | Reporting & Export Improvements | Improve CSV and PDF-ready reporting, column selection, date filters, and export feedback. | UI + Backend | Medium | Medium | Pending |  | 2026-10-06 | 2026-10-08 | 3 | 24 |  | 24 | 36 | No | None | Filtered report query, export job state, and download response
PERF-001 | Connected Enterprise ¦ Overall UI | Performance & Loading Polish | Add loading skeletons, debounce expensive filters, and optimize large-table rendering. | UI | Medium | Medium | Pending |  | 2026-10-09 | 2026-10-13 | 3 | 24 |  | 24 | 41 | No | UI-001 | Loading states, filter performance, and large-list rendering metrics
QSR-001 | Project QSR ¦ IT/OT Devices | Live IT/OT Device Inventory | Connect the QSR device page to the live inventory snapshot and enforce strict branch fleet separation. | UI + Backend | High | Medium | Pending |  | 2026-09-07 | 2026-09-11 | 5 | 40 |  | 40 | 9 | No | None | GET /api/devices/snapshot and SSE stream; McKinney/Plano source mapping
QSR-002 | Project QSR ¦ Device Telemetry | Device Telemetry History & Trends | Add per-device historical telemetry charts and clear last-seen and connection indicators. | UI + Backend | High | Medium | Pending |  | 2026-09-14 | 2026-09-17 | 4 | 32 |  | 32 | 15 | No | QSR-001 | GET /api/devices/telemetry/history; RSSI and byte-counter series
QSR-003 | Project QSR ¦ Device Controls | Matter / Shelly Device Controls | Complete safe control flows for Matter and Shelly devices with optimistic state and failure recovery. | UI + Backend | Medium | Medium | Pending |  | 2026-09-14 | 2026-09-16 | 3 | 24 |  | 24 | 14 | No | QSR-001 | POST control endpoints, action acknowledgement, and revert-on-failure behavior
QSR-004 | Project QSR ¦ Dynamic Failover | Dynamic Failover Controls | Wire Fiber, 5G, Auto, and per-tunnel path controls to gateway acknowledgement states. | UI + Backend | High | High | Pending |  | 2026-09-18 | 2026-09-24 | 5 | 40 |  | 40 | 22 | No | None | POST /api/gateway/path; 200 ack, 202 pending, and 502 rejection states
QSR-005 | Project QSR ¦ Application Routing | Application-Aware Routing Policy CRUD | Replace policy mocks with create, edit, delete, toggle, and validation flows against the routing API. | UI + Backend | High | Medium | Pending |  | 2026-09-21 | 2026-09-25 | 5 | 40 |  | 40 | 23 | No | None | Policy list, CRUD payloads, enable/disable persistence, and validation
QSR-006 | Project QSR ¦ AI Operations | AI Network Insight / Operator Readout | Add an operator-friendly AI readout for live device and tunnel conditions with graceful no-data handling. | UI + Backend | Medium | High | Pending |  | 2026-09-28 | 2026-10-01 | 4 | 32 |  | 32 | 29 | No | QSR-001; QSR-004 | Insight SSE stream, 503/409 messaging, and current snapshot context
QSR-007 | Project QSR ¦ Fleet Separation | McKinney / Plano Fleet Separation | Make the two QSR site views explicit and prevent mixed gateway or device data across branch pages. | UI + Backend | High | Medium | Pending |  | 2026-09-28 | 2026-09-30 | 3 | 24 |  | 24 | 28 | No | QSR-001 | b-mck-03 and b-pln-01 source contracts; strict equality filters
QSR-008 | Project QSR ¦ Gateway Reliability | Gateway Feed Health & Reconnect UX | Show feed freshness, reconnect attempts, waiting states, and operator guidance when a gateway is offline. | UI | Medium | Medium | Pending |  | 2026-10-02 | 2026-10-06 | 3 | 24 |  | 24 | 34 | No | QSR-001 | SSE heartbeat state, last snapshot timestamp, and reconnect status
QSR-009 | Project QSR ¦ Deployment | QSR Deployment & Auth Hardening | Harden reverse-proxy, operator authentication, buffering, and service deployment configuration. | Backend | High | High | Pending |  | 2026-10-05 | 2026-10-08 | 4 | 32 |  | 32 | 36 | No | QSR-004 | Nginx proxy rules, operator header, service unit, and secret handling
QSR-010 | Project QSR ¦ Verification | Simulator & Integration Test Coverage | Add repeatable inventory, control, failover, and no-gateway tests for the combined QSR packs. | UI + Backend | Medium | Medium | Pending |  | 2026-10-09 | 2026-10-14 | 4 | 32 |  | 32 | 42 | No | QSR-001; QSR-004 | Device simulators, route tests, SSE assertions, and integration checklist
SF-001 | Smart Factory ¦ Site Onboarding | Factory Site Onboarding Flow | Create a guided flow to register a plant, assign an authorized site, and confirm the first gateway operation. | UI + Backend | High | Medium | Pending |  | 2026-10-15 | 2026-10-21 | 5 | 40 |  | 40 | 49 | No | None | Site record, tenant assignment, gateway claim, and operation progress
SF-002 | Smart Factory ¦ Gateway Provisioning | Manufacturing Gateway Provisioning & Certificate Binding | Complete secure factory serial verification, certificate binding, and operational identity handoff. | Backend | High | High | Pending |  | 2026-10-15 | 2026-10-22 | 6 | 48 |  | 48 | 50 | No | SF-001 | Unique bootstrap identity, manufacturing record, certificate status, and CAS checks
SF-003 | Smart Factory ¦ OT Discovery | OT Device Discovery & Classification | Discover factory-floor devices and classify equipment by OT role, line, and criticality. | UI + Backend | High | Medium | Pending |  | 2026-10-22 | 2026-10-28 | 5 | 40 |  | 40 | 56 | No | SF-002 | Device inventory, OT tags, asset metadata, and classification overrides
SF-004 | Smart Factory ¦ Digital Twin | Production Line Digital Twin UI | Build a visual twin of plant lines, gateways, machines, and current operating health. | UI | High | High | Pending |  | 2026-10-22 | 2026-10-30 | 7 | 56 |  | 56 | 58 | No | SF-003 | Line hierarchy, machine relationships, health state, and drill-down panels
SF-005 | Smart Factory ¦ Live Telemetry | Real-time Machine Telemetry Dashboard | Surface live temperature, vibration, throughput, run state, and last-seen metrics for production assets. | UI + Backend | High | High | Pending |  | 2026-11-02 | 2026-11-09 | 6 | 48 |  | 48 | 68 | No | SF-003 | Telemetry stream, metric units, thresholds, time series, and freshness state
SF-006 | Smart Factory ¦ Predictive Maintenance | Predictive Maintenance Signals | Add maintenance risk indicators, anomaly summaries, and recommended next actions for assets. | UI + Backend | Medium | High | Pending |  | 2026-11-02 | 2026-11-09 | 6 | 48 |  | 48 | 68 | No | SF-005 | Anomaly scores, maintenance windows, asset history, and action recommendations
SF-007 | Smart Factory ¦ Energy | Energy & Utility Monitoring | Track plant energy use, peak demand, utility status, and opportunities for idle-load reduction. | UI + Backend | Medium | Medium | Pending |  | 2026-11-10 | 2026-11-13 | 4 | 32 |  | 32 | 72 | No | SF-005 | Meter readings, utility feeds, cost rates, and baseline comparisons
SF-008 | Smart Factory ¦ Alarms | Incident / Alarm Workflow with Escalation | Create severity-aware alarm workflows with acknowledgement, escalation timers, and shift handoff. | UI + Backend | High | Medium | Pending |  | 2026-11-10 | 2026-11-16 | 5 | 40 |  | 40 | 75 | No | SF-005 | Alarm events, severity, acknowledgement, escalation policy, and audit trail
SF-009 | Smart Factory ¦ Governance | Role-based Operations Views & Audit Log | Add role-aware plant views and a searchable audit trail for controls, configuration, and approvals. | UI + Backend | Medium | Medium | Pending |  | 2026-11-17 | 2026-11-20 | 4 | 32 |  | 32 | 79 | No | SF-001 | Roles, permissions, operator identity, change events, and retention
SF-010 | Smart Factory ¦ Operations | Factory Deployment Observability & Runbooks | Prepare health checks, deployment dashboards, rollback guidance, and operator runbooks for plant rollout. | DevOps | Medium | Medium | Pending |  | 2026-11-17 | 2026-11-20 | 4 | 32 |  | 32 | 79 | No | SF-002; SF-008 | Service health, deployment state, alerts, rollback steps, and support ownership
Formulas:
Days Left = IF([Activity]="","",IF([Due Date]="","",[Due Date]-TODAY()))
Overdue? = IF([Activity]="","",IF(OR([Status]="Completed",[Due Date]=""),"",IF([Due Date]<TODAY(),"Yes","No")))

## Lists & Guide
Lists & Guide
Status | Priority | Complexity | Type | Assumption
Pending | High | High | UI | Hours per workday
In Progress | Medium | Medium | Backend | 8
Blocked | Low | Low | UI + Backend
On Hold | P1 - Critical |  | DevOps
Completed
How to use
1. Update Status, Owner, Actual Hours, Due Date, and Notes in Activity Tracker.
2. Remaining Hours, Days Left, Overdue?, and Dashboard totals update automatically.
3. Est. Hours is calculated as Est. Days × Hours per workday.
4. Overdue? compares Due Date with today's date and ignores Completed activities.
5. Starter set includes 10 tasks each for Connected Enterprise, Project QSR, and Smart Factory, based on the workspace references and requested themes.